## Cover
Test Report
Project | Website Fahasa bán sách
Program / Division | FAHASA_2025
Author / Technical Owner | Nguyễn Hoàng Hiếu, Lâm Diệu Quang
Approval Status | Not Required
Reporting date | 2025-10-12
For more information
Name
Title
IBM address
Telephone
Fax
E-mail
Template Used:
Test Report.xls 1.0

## Test Report
Test Report
Project |  | Evershop Shoes Store
Build Version |  | 1
Report Date |  | 21/12/2025
Prepared by |  | Châu Gia Anh, Dương Lê Khánh, Đào Thị Thanh Tâm
Phạm vi báo cáo |  | Module Authentication (Kiểm soát bảo mật)
1. Test Execution Summary
Category | Total Tests | Passed | Failed | Pass Rate | Remarks
E2E (Cypress) | 222 | 177 | 45 | 79.7% | Focused on user flows, UI, and security; issues in access control and security.
Unit/Integration | 105 | 93 | 12 | 88.6% | Focused on session config and store; mock dependency issues.
Total | 327 | 270 | 57 | 82.6% | Overall stable but security risks need immediate fix. Time: E2E 10:11 min, Unit 4.534 sec.
2.1 Test Environment
Environment | Description | Remarks
E2E | Cypress on local/development server; browsers: Chrome/Edge; OS: Windows/Mac | Simulated real user interactions; no production data used.
Unit | Jest framework; NODE_ENV='test'; mocked dependencies | Coverage 100%; warnings on config files.
2.2 Test Coverage Summary
Description | # Test Cases | Remarks
Admin Access Control | 32 | 56.3% pass; high failure in authorization rules.
Admin Login | 39 | 94.9% pass; minor edge cases failed.
Admin Logout | 25 | 76.0% pass; session cleanup issues.
Auth Flow | 23 | 91.3% pass; timing issues in cycles.
Auth Security | 30 | 60.0% pass; critical failures in CSRF/XSS/SQL.
Customer Login | 45 | 86.7% pass; form validation errors.
Customer Logout | 28 | 89.3% pass; cached credentials not cleared.
Session Config (Unit) | 105 | 88.6% pass; 100% coverage but mock failures.
Total Coverage | 327 | 100% for unit; E2E focuses on end-to-end paths.
2.3 Defect Summary
Defect Severity | # Defects | Description | Remarks
High (🔴) | 2 | Security (CSRF/XSS/SQL Injection) & Access Control failures. | Immediate fix required; affects system integrity.
Medium (🟡) | 2 | Session cleanup & config handling (resave/saveUninitialized). | Impacts session management; potential reuse risks.
Low (🟢) | 2 | Mock/dependency injection & env config warnings. | Test reliability issues; no production impact.
Total | 6 | Derived from 57 failed tests. | Prioritize security; re-test after fixes.